## Sheet1
Quality Council - action list
Item # | Line # | Topic | Issue | Status
1 | Line 16 | Readmission | Council recommended ACO-8; most payers have programmed NCQA readmission measure (NQF 1768) | Scheduling consultation with NCQA; discuss relative merits of their measure; how do they handle BH, obstetrics as compared to ACO-8; what are they doing in the area of ACO measures more generally?
2 | Line 17 | Readmission | No pediatric readmission measure; consider NQF 2392 | Examine base rates with payers
3 | Line 31, 32 | Asthma | Hospital admission or ED utilization? | Scheduling consultation with NCQA; why are there no NQF endorsed ED use measures whether for asthma or in general? What is their recommendation? What do they have in the pipeline?
4 | Line 18 -25 | Base rates | Are base rates sufficient for SNF readmission, CHF, COPD, Diabetes, Asthma, and mult-condition admission | Conduct base rate analysis with payers; working with Connecticare to develop initial analytic model and template for use by other payers.
5 | Line 65-67, 162-163 | Obstetrics measures | Are such measures appropriate for ACO accountability; is there opportunity for improvement; are proposed areas clinically important/high priority | Scheduling consultation with NCQA; also scheduling consultation with National Perinatal Information Center
6 | Line 68 | Post-partum depression | There is no NQF endorsed measure, perhaps no measure of this; Council discussed CHIPRA endorsed behavioral risk factor screening, which is pre-natal and EMR derived | Consulting with CHF to further research options for post-partum depression screening; Council to reconsider Behavioral Health Risk Assessment (for Pregnant Women) as an alternative
7 | Line 53 | Preventive care and screening: body mass index screening and follow-up | Council questions feasibility of collecting information re: follow-up plan | Dr. Selinger researched how measure is produced by Pro Health; Allscripts EMR modifications were made to enable data capture re: follow-up plan; appears to be feasible to collect and report and most advanced networks should be doing so for Medicare SSP
8 | Line 26 | Percent of primary care physicians who successfully meet meaningful use requirements | This is a Medicare aligned measure that many council members have proposed be dropped due to limited value (check box compliance) and burden of reporting. However, concerns have been raised that the majority of provider organizations that would be participating in SSP are already complying with meaningful use criteria for the Medicare Shared Savings Program. NCQA standards are also currently aligning with the Medicare meaningful use criteria. It is the only measure being reviewed by Quality Council that addresses the IT infrastructure necessary for quality reporting and care coordination activities and there does not seem to be another nationally aligned measure in the set that takes its place. | Under review; next steps TBD